## Master WBS Template
ERP WBS Code | Parent WBS Code | WBS Level | Element Name / Execution Description | Account Head / Ledger Group | Cost Type Category | Indian Statutory / Schedule Classification
UIEPL-INFRA-2026 | None | 1 | Infrastructure Project (Master Project) | CWIP - Master Asset | Mixed | Mixed Project Class
UIEPL-INFRA.01 | UIEPL-INFRA-2026 | 2 | Pre-Construction & Common Infrastructure | Pre-operative Expenses | Mixed | Pre-operative Expense
UIEPL-INFRA.01.01 | UIEPL-INFRA.01 | 3 | Land Acquisition, Registration & Liasoning | Land Asset Account | Govt Fees / Statutory | Non-RERA / Capital Land Cost
UIEPL-INFRA.01.01.01 | UIEPL-INFRA.01.01 | 4 | - Land Title Search, Due Diligence & Legal Clearances | Legal & Professional Fees | Consultant Charges | Non-RERA / Capital Land Cost
UIEPL-INFRA.01.01.02 | UIEPL-INFRA.01.01 | 4 | - Compensations, Registry & Stamp Duty Payments | Land Asset Account | Govt Fees / Statutory | Non-RERA / Capital Land Cost
UIEPL-INFRA.01.01.03 | UIEPL-INFRA.01.01 | 4 | - Boundary Demarcation & Surveying (DGPS/GIS Mapping) | Survey & Engineering Fees | Consultant Charges | Non-RERA / Capital Land Cost
UIEPL-INFRA.01.02 | UIEPL-INFRA.01 | 3 | Statutory Approvals & Clearances | Statutory Fees Ledger | Govt Fees / Challan | RERA Eligible / Statutory Fees
UIEPL-INFRA.01.02.01 | UIEPL-INFRA.01.02 | 4 | - Environmental Impact Assessment (EIA) & Pollution Board NOC | Statutory Fees Ledger | Govt Fees / Challan | RERA Eligible / Statutory Fees
UIEPL-INFRA.01.02.02 | UIEPL-INFRA.01.02 | 4 | - Municipal Corporation Sanction Plan Approvals & Fire NOC | Statutory Fees Ledger | Govt Fees / Challan | RERA Eligible / Statutory Fees
UIEPL-INFRA.01.02.03 | UIEPL-INFRA.01.02 | 4 | - RERA Registration & Project Portal Activation | Statutory Fees Ledger | Govt Fees / Challan | RERA Eligible / Statutory Fees
UIEPL-INFRA.01.03 | UIEPL-INFRA.01 | 3 | Detailed Project Report (DPR) & Engineering Design | Professional Fees | Consultant Charges | RERA Eligible / Professional Fees
UIEPL-INFRA.01.03.01 | UIEPL-INFRA.01.03 | 4 | - Geotechnical & Soil Investigation Works | Geotech Testing Ledger | Consultant Charges | RERA Eligible / Professional Fees
UIEPL-INFRA.01.03.02 | UIEPL-INFRA.01.03 | 4 | - Architectural Concept & Detailed Good for Construction (GFC) Drawings | Professional Fees | Consultant Charges | RERA Eligible / Professional Fees
UIEPL-INFRA.01.03.03 | UIEPL-INFRA.01.03 | 4 | - Structural Design, Peer Review & Third-Party IIT Validation | Professional Fees | Consultant Charges | RERA Eligible / Professional Fees
UIEPL-INFRA.01.04 | UIEPL-INFRA.01 | 3 | Site Mobilization & Temporary Infrastructure | Temporary Structures CWIP | Materials & Labor | RERA Eligible / Mobilization Advance
UIEPL-INFRA.01.04.01 | UIEPL-INFRA.01.04 | 4 | - Site Fencing, Gateways & Security Cabin Setup | Temporary Structures CWIP | Materials & Labor | RERA Eligible / Infra Cost
UIEPL-INFRA.01.04.02 | UIEPL-INFRA.01.04 | 4 | - Labor Camp Construction, Sanitation & Drinking Water Facilities | Labor Welfare Expense | Materials & Labor | RERA Eligible / Infra Cost
UIEPL-INFRA.01.04.03 | UIEPL-INFRA.01.04 | 4 | - Site Office, Stores & Concrete Batching Plant Commissioning | Temporary Structures CWIP | Machinery Rental & Setup | RERA Eligible / Infra Cost
UIEPL-INFRA.01.05 | UIEPL-INFRA.01 | 3 | Utility Shifting & Power Line Clearance | Utility Shifting Expense | Subcontractor / Liaison | Infrastructure Cost Item
UIEPL-INFRA.01.05.01 | UIEPL-INFRA.01.05 | 4 | - High Tension (HT) Power Line & Transformer Shifting | Utility Shifting Expense | Subcontractor / Liaison | Infrastructure Cost Item
UIEPL-INFRA.01.05.02 | UIEPL-INFRA.01.05 | 4 | - Water Supply, Sewage & Telecom Line Relocation | Utility Shifting Expense | Subcontractor / Liaison | Infrastructure Cost Item
UIEPL-INFRA.02 | UIEPL-INFRA | 2 | Building Construction Vertical (Residential / Commercial / Terminal) | CWIP - Building Structure | Mixed | RERA Eligible Construction Cost
UIEPL-INFRA.02.01 | UIEPL-INFRA.02 | 3 | Substructure & Foundation Engineering | Building Concrete & Steel CWIP | Materials & Labor | RERA Eligible / Substructure
UIEPL-INFRA.02.01.01 | UIEPL-INFRA.02.01 | 4 | - Mass Bulk Excavation & Backfilling | Earthwork Expense | Machinery Rental & Labor | RERA Eligible / Substructure
UIEPL-INFRA.02.01.02 | UIEPL-INFRA.02.01 | 4 | - Bored Cast-in-Situ Piling Works & Pile Integrity Testing (PIT) | Piling Work Ledger | Subcontractor / Labor | RERA Eligible / Substructure
UIEPL-INFRA.02.01.03 | UIEPL-INFRA.02.01 | 4 | - Plain Cement Concrete (PCC) Mat & Anti-Termite Treatment | Building Concrete CWIP | Material (Cement/Aggregates) | RERA Eligible / Substructure
UIEPL-INFRA.02.01.04 | UIEPL-INFRA.02.01 | 4 | - Reinforced Cement Concrete (RCC) Raft Foundation Casting | Building Concrete & Steel CWIP | Material (Concrete/Rebar) | RERA Eligible / Substructure
UIEPL-INFRA.02.01.05 | UIEPL-INFRA.02.01 | 4 | - Basement Retaining Wall Construction & Multi-layer Waterproofing | Waterproofing Ledger | Material & Subcontractor | RERA Eligible / Substructure
UIEPL-INFRA.02.02 | UIEPL-INFRA.02 | 3 | Superstructure Structural Works (RCC Frame) | Building Concrete & Steel CWIP | Material (Cement/Steel) | RERA Eligible / Structure
UIEPL-INFRA.02.02.01 | UIEPL-INFRA.02.02 | 4 | - Columns & Shear Walls Reinforcement Binding & Formwork Staging | Structural Labor Ledger | PRW Labor / Subcontractor | RERA Eligible / Structure
UIEPL-INFRA.02.02.02 | UIEPL-INFRA.02.02 | 4 | - Ready-Mix Concrete (RMC) Pouring for Columns & Cure Monitoring | Building Concrete CWIP | Material (Concrete) | RERA Eligible / Structure
UIEPL-INFRA.02.02.03 | UIEPL-INFRA.02.02 | 4 | - Floor Beams & Slab Shuttering, Centering & Reinforcement Fixing | Structural Labor Ledger | PRW Labor / Subcontractor | RERA Eligible / Structure
UIEPL-INFRA.02.02.04 | UIEPL-INFRA.02.02 | 4 | - Slab Casting, Laser Screed Finishing & Post-Pour Curing | Building Concrete CWIP | Material (Concrete) | RERA Eligible / Structure
UIEPL-INFRA.02.02.05 | UIEPL-INFRA.02.02 | 4 | - Post-Tensioning (PT) Strand Threading, Grouting & Jacking Work | PT Specialist Ledger | Specialist Contractor | RERA Eligible / Structure
UIEPL-INFRA.02.03 | UIEPL-INFRA.02 | 3 | Masonry, Internal Plastering & Drywall Core | Building Finishing CWIP | Material & PRW Labor | RERA Eligible / Finishes
UIEPL-INFRA.02.03.01 | UIEPL-INFRA.02.03 | 4 | - AAC Block Work / Fly Ash Brickwork with Jointing Mortar | Masonry Ledger | Material & Labor | RERA Eligible / Finishes
UIEPL-INFRA.02.03.02 | UIEPL-INFRA.02.03 | 4 | - Internal Walls Sand-Face Plastering & Gypsum Punning Base | Masonry Ledger | Material & Labor | RERA Eligible / Finishes
UIEPL-INFRA.02.03.03 | UIEPL-INFRA.02.03 | 4 | - External Wall Double-Coat Waterproof Plastering | Masonry Ledger | Subcontractor / Material | RERA Eligible / Finishes
UIEPL-INFRA.02.04 | UIEPL-INFRA.02 | 3 | MEP Integration & Services Framework | MEP Asset Ledger | Equipment & Subcontractor | RERA Eligible / Services (18% GST)
UIEPL-INFRA.02.04.01 | UIEPL-INFRA.02.04 | 4 | - Plumbing & Sanitary Concealed Piping, Vertical Stacks & Drainage | Plumbing Works | Material & PRW Labor | RERA Eligible / Services
UIEPL-INFRA.02.04.02 | UIEPL-INFRA.02.04 | 4 | - Electrical Conduit Laying, DB Dressing & Wire Pulling (FRLS) | Electrical Works | Material & PRW Labor | RERA Eligible / Services
UIEPL-INFRA.02.04.03 | UIEPL-INFRA.02.04 | 4 | - HVAC Chilled Water Piping, Ducting Fabrication & AHU Installation | HVAC Asset Ledger | Equipment & Installation | RERA Eligible / Services
UIEPL-INFRA.02.04.04 | UIEPL-INFRA.02.04 | 4 | - Fire Sprinkler Main Lines, Wet Risers & Fire Pump Room Assembly | Fire Fighting Ledger | Equipment & Installation | RERA Eligible / Services
UIEPL-INFRA.02.04.05 | UIEPL-INFRA.02.04 | 4 | - ELV Systems (CCTV, Access Control, BMS & Fire Alarm Wiring) | ELV Systems Ledger | Supply & Commissioning | RERA Eligible / Services
UIEPL-INFRA.02.05 | UIEPL-INFRA.02 | 3 | Finishing Works & Architectural Facade | Building Finishing CWIP | Material & Subcontractor | RERA Eligible / Architectural Finishes
UIEPL-INFRA.02.05.01 | UIEPL-INFRA.02.05 | 4 | - Vitrified Tiling / Italian Marble Flooring Laying & Diamond Polishing | Flooring Expense | Material & Labor | RERA Eligible / Architectural Finishes
UIEPL-INFRA.02.05.02 | UIEPL-INFRA.02.05 | 4 | - Internal Wall Painting (Putty Base, Primer & Acrylic Emulsion) | Painting Expense | Material & Labor | RERA Eligible / Architectural Finishes
UIEPL-INFRA.02.05.03 | UIEPL-INFRA.02.05 | 4 | - External Facade Structural Glazing, Spider Fittings & ACP Cladding | Facade Expense | Specialist Contractor | RERA Eligible / Architectural Finishes
UIEPL-INFRA.02.05.04 | UIEPL-INFRA.02.05 | 4 | - Doors & Windows Joinery Frames, Fire-Rated Flush Doors & UPVC Casements | Joinery Ledger | Material & Labor | RERA Eligible / Architectural Finishes
UIEPL-INFRA.03 | UIEPL-INFRA | 2 | Roads & Highways Infrastructure Vertical | CWIP - Roads & Highways | Mixed | NHAI / MoRTH Schedule Item
UIEPL-INFRA.03.01 | UIEPL-INFRA.03 | 3 | Earthwork, Clearing & Subgrade Preparation | Earthwork Expense | Machinery Rental & Labor | MoRTH Section 200
UIEPL-INFRA.03.01.01 | UIEPL-INFRA.03.01 | 4 | - Clearing and Grubbing of Road Right of Way (ROW) | Earthwork Expense | Machinery Rental & Labor | MoRTH Section 201
UIEPL-INFRA.03.01.02 | UIEPL-INFRA.03.01 | 4 | - Excavation in Cutting & Borrow Area Soil Haulage | Earthwork Expense | Machinery Rental & Labor | MoRTH Section 202
UIEPL-INFRA.03.01.03 | UIEPL-INFRA.03.01 | 4 | - Embankment & Subgrade Compaction to Specified MDD Ratios | Earthwork Expense | Machinery Rental & Labor | MoRTH Section 203
UIEPL-INFRA.03.02 | UIEPL-INFRA.03 | 3 | Granular Base & Sub-Base Layers (Flexible/Rigid) | Flexible Pavement CWIP | Material (Aggregates) | MoRTH Section 400
UIEPL-INFRA.03.02.01 | UIEPL-INFRA.03.02 | 4 | - Granular Sub-Base (GSB) Laying, Grading & Smooth-Wheel Rolling | Flexible Pavement CWIP | Material & Machinery | MoRTH Section 401
UIEPL-INFRA.03.02.02 | UIEPL-INFRA.03.02 | 4 | - Wet Mix Macadam (WMM) Preparation, Spreading & Compaction | Flexible Pavement CWIP | Material & Machinery | MoRTH Section 406
UIEPL-INFRA.03.03 | UIEPL-INFRA.03 | 3 | Bituminous Base Course & Wearing Surface | Flexible Pavement CWIP | Bitumen Material & Laying | MoRTH Section 500
UIEPL-INFRA.03.03.01 | UIEPL-INFRA.03.03 | 4 | - Application of Bituminous Prime Coat & Tack Coat Emulsions | Flexible Pavement CWIP | Material (Bitumen/Emulsion) | MoRTH Section 502 / 503
UIEPL-INFRA.03.03.02 | UIEPL-INFRA.03.03 | 4 | - Dense Bituminous Macadam (DBM) Batch Mixing & Paver Laying | Flexible Pavement CWIP | Material & Laying Cost | MoRTH Section 505
UIEPL-INFRA.03.03.03 | UIEPL-INFRA.03.03 | 4 | - Bituminous Concrete (BC) Surfacing & Pneumatic Tyre Rolling | Flexible Pavement CWIP | Material & Laying Cost | MoRTH Section 507
UIEPL-INFRA.03.04 | UIEPL-INFRA.03 | 3 | Rigid Concrete Pavement Core (PQC) | Rigid Pavement CWIP | Cement & Admixture Material | MoRTH Section 600
UIEPL-INFRA.03.04.01 | UIEPL-INFRA.03.04 | 4 | - Dry Lean Concrete (DLC) Sub-base Laying & Finishing | Rigid Pavement CWIP | Concrete Material | MoRTH Section 601
UIEPL-INFRA.03.04.02 | UIEPL-INFRA.03.04 | 4 | - Pavement Quality Concrete (PQC) Fixed/Slipform Paver Operations | Rigid Pavement CWIP | Material (High-Grade Concrete) | MoRTH Section 602
UIEPL-INFRA.03.04.03 | UIEPL-INFRA.03.04 | 4 | - Dowel Bar & Tie Bar Insertion, Groove Cutting & Joint Sealing | Rigid Pavement CWIP | Material & Subcontractor | MoRTH Section 602.1
UIEPL-INFRA.03.05 | UIEPL-INFRA.03 | 3 | Road Furniture, Safety Markings & HTMS System | Road Appurtenances Ledger | Supply & Installation | MoRTH Section 800
UIEPL-INFRA.03.05.01 | UIEPL-INFRA.03.05 | 4 | - Thermoplastic Road Marking Application & Cat-Eyes Installation | Road Appurtenances Ledger | Material & Labor | MoRTH Section 803
UIEPL-INFRA.03.05.02 | UIEPL-INFRA.03.05 | 4 | - Retro-Reflective Signages & W-Beam Metal Crash Barrier Fixing | Road Appurtenances Ledger | Supply & Subcontractor | MoRTH Section 804 / 811
UIEPL-INFRA.03.05.03 | UIEPL-INFRA.03.05 | 4 | - Highway Traffic Management System (HTMS), ATCC & Toll Plaza IT | IT Infrastructure Ledger | Equipment Procurement | HTMS Technology Pack
UIEPL-INFRA.04 | UIEPL-INFRA | 2 | Bridges & Flyovers Engineering Vertical | CWIP - Bridges & Structures | Mixed | NHAI / MoRTH Bridge Schedule
UIEPL-INFRA.04.01 | UIEPL-INFRA.04 | 3 | Substructure Deep Foundation Works | Bridge Structural CWIP | Concrete, Steel & PRW Labor | MoRTH Section 1100 / Foundations
UIEPL-INFRA.04.01.01 | UIEPL-INFRA.04.01 | 4 | - Large Diameter Pile Boring & Polymer Slurry Circulation | Bridge Structural CWIP | Machinery Rental & Labor | MoRTH Section 1115
UIEPL-INFRA.04.01.02 | UIEPL-INFRA.04.01 | 4 | - Heavy Cage Fabrications, Sonic Logging Tube Layout & Lowering | Bridge Structural CWIP | Material & Labor | MoRTH Section 1116
UIEPL-INFRA.04.01.03 | UIEPL-INFRA.04.01 | 4 | - Underwater Tremie Concrete Pouring & Pile Head Chipping Work | Bridge Structural CWIP | Concrete Material | MoRTH Section 1117
UIEPL-INFRA.04.01.04 | UIEPL-INFRA.04.01 | 4 | - Pile Cap Excavation, High-Yield Rebar Binding & Monolithic Casting | Bridge Structural CWIP | Material & Labor | MoRTH Section 1120
UIEPL-INFRA.04.02 | UIEPL-INFRA.04 | 3 | Substructure Pier Columns & Abutment Walls | Bridge Structural CWIP | Formwork, Reinforcement & Concrete | MoRTH Section 1200 / Piers
UIEPL-INFRA.04.02.01 | UIEPL-INFRA.04.02 | 4 | - Tall Pier Formwork Assembly & Climbing Shuttering Configuration | Bridge Structural CWIP | Subcontractor / Equipment | MoRTH Section 1204
UIEPL-INFRA.04.02.02 | UIEPL-INFRA.04.02 | 4 | - Pier Reinforcement Cage Lowering, In-situ Casting & Curing | Bridge Structural CWIP | Material & Labor | MoRTH Section 1205
UIEPL-INFRA.04.02.03 | UIEPL-INFRA.04.02 | 4 | - Pier Cap Structural Casting & Pedestal Level Alignment Checks | Bridge Structural CWIP | Material & Labor | MoRTH Section 1206
UIEPL-INFRA.04.03 | UIEPL-INFRA.04 | 3 | Superstructure Girder Fabrication & Post-Tensioning | Bridge Structural CWIP | Prestressing & Subcontractor | MoRTH Section 1500 / Girders
UIEPL-INFRA.04.03.01 | UIEPL-INFRA.04.03 | 4 | - Pre-cast Segment Casting Yard Setup & Jig Formwork Management | Casting Yard Expense | Setup & Material | MoRTH Section 1503
UIEPL-INFRA.04.03.02 | UIEPL-INFRA.04.03 | 4 | - PSC Girder Casting, Steam Curing & High Tensile Wire Threading | Bridge Structural CWIP | Material & Labor | MoRTH Section 1504
UIEPL-INFRA.04.03.03 | UIEPL-INFRA.04.03 | 4 | - Hydraulic Post-Tensioning Jacking, Elongation Logging & Grouting | Bridge Structural CWIP | Specialist Contractor | MoRTH Section 1505
UIEPL-INFRA.04.03.04 | UIEPL-INFRA.04.03 | 4 | - Heavy Launching Girder (Gantry) Assembly & Girder Segment Erection | Erection Expense Ledger | Machinery Rental & Labor | MoRTH Section 1507
UIEPL-INFRA.04.04 | UIEPL-INFRA.04 | 3 | Superstructure Deck Construction & Finishes | Bridge Structural CWIP | Material & Labor | MoRTH Section 1600 / Deck
UIEPL-INFRA.04.04.01 | UIEPL-INFRA.04.04 | 4 | - Girder Stitching, Diaphragm Reinforcement & Casting | Bridge Structural CWIP | Material & Labor | MoRTH Section 1603
UIEPL-INFRA.04.04.02 | UIEPL-INFRA.04.04 | 4 | - Deck Slab Shuttering, Crash Barrier Mesh Layout & Casting Run | Bridge Structural CWIP | Material & Labor | MoRTH Section 1605
UIEPL-INFRA.04.04.03 | UIEPL-INFRA.04.04 | 4 | - Bridge Deck Multi-layer Waterproofing & Mastic Asphalt Wearing Layer | Bridge Finishing CWIP | Material & Subcontractor | MoRTH Section 1608
UIEPL-INFRA.04.05 | UIEPL-INFRA.04 | 3 | Bridge Structural Appurtenances & Bearings | Bridge Component Ledger | Specialist Supply & Fit | MoRTH Section 2000 / Bearings
UIEPL-INFRA.04.05.01 | UIEPL-INFRA.04.05 | 4 | - POT-PTFE / Elastomeric Bearing Procurement, Seating & Fixing | Bridge Component Ledger | Material Procurement | MoRTH Section 2002
UIEPL-INFRA.04.05.02 | UIEPL-INFRA.04.05 | 4 | - Expansion Joint Assembly (Strip Seal / Modular) Fixing | Bridge Component Ledger | Material & Subcontractor | MoRTH Section 2004
UIEPL-INFRA.05 | UIEPL-INFRA | 2 | Tunnel & Underground Infrastructure Vertical | CWIP - Tunnels | Mixed | Underground Infra Special Class
UIEPL-INFRA.05.01 | UIEPL-INFRA.05 | 3 | Tunnel Portals & Shaft Engineering | Tunnel Civil CWIP | Subcontractor & Machinery | Underground Civil Work
UIEPL-INFRA.05.01.01 | UIEPL-INFRA.05.01 | 4 | - Portal Slope Stabilization, Soil Nailing & Consolidation Grouting | Tunnel Civil CWIP | Subcontractor & Material | Tunnel Portal Stability
UIEPL-INFRA.05.01.02 | UIEPL-INFRA.05.01 | 4 | - TBM Launch / Retrieval Shaft Excavation & Secant Piling Support | Tunnel Shaft Ledger | Machinery Rental & Labor | TBM Shaft Engineering
UIEPL-INFRA.05.02 | UIEPL-INFRA.05 | 3 | Tunnel Drive Excavation (NATM / TBM) | Tunnel Drilling Ledger | Explosives, Consumables & Labor | Excavation Run-Meter Cost
UIEPL-INFRA.05.02.01 | UIEPL-INFRA.05.02 | 4 | - NATM Face Drilling, Explosive Charging, Blasting & Mucking Runs | Tunnel Drilling Ledger | Consumables & Labor | NATM Excavation Mode
UIEPL-INFRA.05.02.02 | UIEPL-INFRA.05.02 | 4 | - TBM Cutterhead Assembly, Main Drive Shield Advance & Muck Ring Conveyor | TBM Operation Ledger | Machinery Ops & Consumables | TBM Tunneling Mode
UIEPL-INFRA.05.02.03 | UIEPL-INFRA.05.02 | 4 | - Pre-cast Concrete Tunnel Segment Ring Lining Erector Operations | TBM Operation Ledger | Material (Precast Segments) | TBM Ring Segment Lining
UIEPL-INFRA.05.03 | UIEPL-INFRA.05 | 3 | Primary Structural Tunnel Support Support (NATM Focus) | Tunnel Support CWIP | Steel & Cement Material | Tunnel Stabilization Cost
UIEPL-INFRA.05.03.01 | UIEPL-INFRA.05.03 | 4 | - Application of Primary Robot Shotcreted Concrete (Fibre Reinforced) | Tunnel Support CWIP | Material & Machinery Ops | Tunnel Primary Support
UIEPL-INFRA.05.03.02 | UIEPL-INFRA.05.03 | 4 | - Swellex / Rock Bolt Drilling, Insertion & Resin Capsule Grouting | Tunnel Support CWIP | Material & Labor | Tunnel Rock Bolting Matrix
UIEPL-INFRA.05.03.03 | UIEPL-INFRA.05.03 | 4 | - Lattice Girder / Steel Rib Fitting, Alignment Shimming & Anchoring | Tunnel Support CWIP | Material & Labor | Tunnel Arch Rib Support
UIEPL-INFRA.05.04 | UIEPL-INFRA.05 | 3 | Waterproofing & Secondary Permanent Lining | Tunnel Structural CWIP | Concrete Lining Material | Waterproofing / Permanent Lining
UIEPL-INFRA.05.04.01 | UIEPL-INFRA.05.04 | 4 | - PVC Geotextile Membrane Layout & Thermal Welding Configuration | Tunnel Structural CWIP | Material & Subcontractor | Tunnel Waterproofing Layer
UIEPL-INFRA.05.04.02 | UIEPL-INFRA.05.04 | 4 | - Hydraulic Shuttering Gantry Mobilization & Reinforcement Framework | Tunnel Structural CWIP | Machinery Rental & Labor | Tunnel Secondary Lining
UIEPL-INFRA.05.04.03 | UIEPL-INFRA.05.04 | 4 | - Secondary Arch RCC Lining Pouring, Consolidation Grouting & Plugs | Tunnel Structural CWIP | Material (Concrete) | Tunnel Secondary Lining
UIEPL-INFRA.05.05 | UIEPL-INFRA.05 | 3 | Tunnel Electro-Mechanical (E&M) Systems Integration | Tunnel E&M Ledger | Electro-Mechanical Equipment | E&M Systems (High Import/GST Risk)
UIEPL-INFRA.05.05.01 | UIEPL-INFRA.05.05 | 4 | - Tunnel Jet Fan Ventilation Array Installation & Power Drop Connections | Tunnel E&M Ledger | Equipment & Installation | Tunnel Ventilation Fan Pack
UIEPL-INFRA.05.05.02 | UIEPL-INFRA.05.05 | 4 | - Linear Heat Detection (LHD) Wiring, Fire Hydrants & Deluge System | Tunnel E&M Ledger | Equipment & Installation | Tunnel Fire Life Safety Systems
UIEPL-INFRA.05.05.03 | UIEPL-INFRA.05.05 | 4 | - SCADA Control Automation Integration, Fiber Backbone & Escape Signages | Tunnel E&M Ledger | System Integration Pack | Tunnel Automation Technology
UIEPL-INFRA.06 | UIEPL-INFRA | 2 | Project Commissioning, Audit & Handover Phase | Pre-operative Expenses | Mixed | Closeout Expense Category
UIEPL-INFRA.06.01 | UIEPL-INFRA.06 | 3 | Testing, Integrated Trials & Quality Assurance Audits | Testing & Inspection | Consultant Charges | Safety Audit Compliance
UIEPL-INFRA.06.01.01 | UIEPL-INFRA.06.01 | 4 | - Non-Destructive Testing (NDT), Core Extractions & Structural Integrity Runs, Bridge Load Test | Testing & Inspection | Consultant Charges | Quality Audit Pack
UIEPL-INFRA.06.01.02 | UIEPL-INFRA.06.01 | 4 | - Integrated Systems Operational Dry Trials (MEP, E&M, HTMS) | Testing & Inspection | Internal Labor / Contractor | Systems Operational Signoff
UIEPL-INFRA.06.02 | UIEPL-INFRA.06 | 3 | As-Built Documentation & Statutory Occupancy Permits | Professional Fees | Internal Labor / Consultant | Documentation Item
UIEPL-INFRA.06.02.01 | UIEPL-INFRA.06.02 | 4 | - Compilation of GFC Red-line Markups & As-Built CAD/BIM Model Submissions | Professional Fees | Internal Engineering Labor | Documentation Item
UIEPL-INFRA.06.02.02 | UIEPL-INFRA.06.02 | 4 | - Statutory Final Clearances (Occupancy Certificate, Lift NOC, Chief Fire Auditor Sign off) | Statutory Fees Ledger | Govt Fees / Liaison | Statutory Final Handover Clearances
UIEPL-INFRA.06.03 | UIEPL-INFRA.06 | 3 | Commercial Project Closeout & Final Bill Clearance | Retention Payables | Financial Charges | Commercial Closeout
UIEPL-INFRA.06.03.01 | UIEPL-INFRA.06.03 | 4 | - Subcontractor / Supplier Final Bill Variances Reconciliations & Reconciliation Signoffs | Contract Settlement Head | Subcontractor Invoices | Commercial Closeout Vendor Pack
UIEPL-INFRA.06.03.02 | UIEPL-INFRA.06.03 | 4 | - Client Joint Measurement Sheets Signing, Retention Bank Guarantee Releases & DLP Initiation | Retention Payables | Financial / Bank Fees | DLP Commercial Activation Account